## Product Backlog (SCRUM)
PRODUCT BACKLOG
Project | Billiards Matching Community |  |  |  |  | Created By | Truong Tan Thanh
Sprint | User story | Category | Priority | Estimation (Hour) | Sprint | Status | Description
Sprint 1: Core Authentication & Setup |  |  |  | 36
1 | As an administrator, I want to log in to the system using email and password | New | High | 8 | 1 | To Do
2 | As an administrator, I want to manage club accounts | New | High | 12 | 1 | To Do
3 | As a club manager, I want to register my club with basic information | New | High | 10 | 1 | To Do
4 | As a club manager, I want to log in to my account | New | High | 6 | 1 | To Do
5 | As a user, I want to view a list of clubs | New | Medium | 8 | 1 | To Do
Sprint 2: Club Management |  |  |  | 38
1 | As an administrator, I want to approve or reject club registrations | New | High | 8 | 2 | To do
2 | As a club manager, I want to update my club's profile information | New | High | 10 | 2 | To do
3 | As a club manager, I want to upload images for my club | New | Medium | 12 | 2 | To do
4 | As a user, I want to view detailed information about a specific club | New | Medium | 8 | 2 | To do
5 | As a user, I want to filter clubs by district and street | New | Medium | 10 | 2 | To do
Sprint 3: Booking System |  |  |  | 44
1 | As a club manager, I want to set up available time slots and booking fees | New | High | 12 | 3 | To do
2 | As a user, I want to register an account | New | High | 8 | 3 | To do
3 | As a user, I want to book a time slot at a club and pay via QR code | New | High | 14 | 3 | To do
4 | As a club manager, I want to view all bookings for my club | New | Medium | 10 | 3 | To do
5 | As a club manager, I want to approve or reject booking requests | New | High | 10 | 3 | To do
6 | As a user, I want to view my booking history | New | Medium | 8 | 3 | To do
Sprint 4: Advanced Features |  |  |  | 34
1 | As a club manager, I want to set special pricing for different time slots | New | Medium | 12 | 4 | To do
2 | As a user, I want to cancel my booking | New | High | 8 | 4 | To do
3 | As an administrator, I want to view system-wide statistics | New | Low | 14 | 4 | To do

## Non-functional requirement
Non-functional requirement
Project Name: Billiards matching community | `
Item | Description
Performance | Page load time should be under 3 seconds
Database queries should be optimized to return results in under 500ms
API response time should be under 2 second for 95% of requests
Security | All passwords must be securely hashed using Bcrypt
User authentication using JWT tokens with appropriate expiration
Input validation for all form submissions to prevent injection attacks
UIUX | Responsive design that works on mobile, tablet, and desktop
Consistent styling throughout the application
Maintainability | Code should follow established Ruby on Rails and Vue.js best practices
Documentation for API endpoints and key functionality
Version control (Git) with clear commit messages